SIMATS ENGINEERING (SAVEETHA SCHOOL OF ENGINEERING)

Department of Computer Science and Engineering

CO1 ASSESSMENT TOOL 2  –  Agile Sprint Planning & User Story Workshop

| Course Code: | CSA10 / CSA1023 | Course Title: | Software Engineering |
| --- | --- | --- | --- |
| CO Assessed: | CO1 | Assessment: | Assessment Tool 2 – Agile Sprint Planning & User Story Workshop |
| Weightage: | 20% | Total Marks: | 25 |
| CO1 Statement: | Apply advanced methodologies and agile project management techniques to manage software projects effectively |  |  |
| Student Name: | Nirmal S | Reg. No.: | 192511249 |
| Date: | 09/10/2026 | Duration: | 60 minutes |

Code of Conduct I Nirmal S (192511249) (Name / Reg No) certify that this submission is my original work and that I have adhered to the guidelines specified for this assessment. I understand that any violation of academic integrity rules will result in disciplinary action. Signature of the Student: Nirmal S

Annexure A – Agile Sprint Planning & User Story Workshop

Instructions to Students:

Each student is assigned an individual software project problem statement. Based on the given problem statement, perform an Agile Sprint Planning and User Story Workshop by applying Agile software engineering practices. Prepare a comprehensive sprint planning document covering the following aspects:

Based on the given problem statement, perform an Agile Sprint Planning and User Story Workshop by applying Agile software engineering practices. Prepare a comprehensive sprint planning document covering the following aspects:

- Identify the Project Vision and Stakeholders

  - Define the project's vision, objectives, and identify all key stakeholders involved.

- Create Epics and User Stories

  - Break down the requirements into Epics and formulate well-structured User Stories using the format:
As a <user>, I want <feature>, so that <benefit>.

- Define Acceptance Criteria

  - Write clear and measurable acceptance criteria for each selected user story using the Given–When–Then format or equivalent.

- Prioritize the Product Backlog

  - Organize and prioritize the product backlog based on business value, customer needs, and project dependencies.

- Plan the Sprint Backlog

  - Select high-priority user stories for the first sprint and divide them into actionable development tasks.

- Estimate Effort Using Story Points

  - Assign story points to each selected user story using an appropriate estimation technique (e.g., Fibonacci sequence or Planning Poker) and justify your estimates.

- Present the Sprint Goal and Expected Deliverables

  - Define a clear sprint goal and describe the expected sprint deliverables, including the features to be completed at the end of the sprint.

PROBLEM STATEMENT:

29. Privacy-Preserving Smart Retail Analytics Platform

Industry Context

Retailers use digital analytics to understand customer movement, product demand, inventory, and store operations. Excessive collection of customer data can create privacy concerns while limiting data collection may reduce analytical value.

Problem Statement

Design and develop a Privacy-Preserving Smart Retail Analytics Platform that provides useful operational analytics while minimizing the collection and exposure of personally identifiable information. The platform should integrate event-driven data processing, dashboards, secure APIs, access control, monitoring, testing, and CI/CD. Privacy policies and data-retention controls should be built into the architecture.

Objectives, The platform should:

- Provide real-time retail operational analytics

- Minimize unnecessary collection of customer information

- Implement secure data processing and access control

- Maintain audit trails and retention policies

- Use scalable event-driven services

- Support automated testing and CI/CD

- Address ethical and privacy requirements

Expected Outcomes:

- The proposed platform will:

- Improve retail operational visibility

- Reduce privacy risks

- Support data-driven decision-making

- Improve scalability and reliability

- Strengthen responsible data management

- Reduce manual analytics effort

Problem Statement 29: Privacy-Preserving Smart Retail Analytics Platform

- Identify the Project Vision and Stakeholders

Project Vision: To engineer a cloud-native, privacy-preserving smart retail analytics platform that delivers continuous, real-time operational intelligence (including customer movement trajectories, shelf dwell times, and product demand metrics) while enforcing automated privacy-by-design mechanisms to systematically eliminate personal data exposure and lower manual analytics effort.

### System Objectives:

  - Provide live operational analytics for floor layout and inventory optimization.

  - Minimize unnecessary collection and persistence of customer identity data.

  - Enforce robust data encryption, secure APIs, and role-based access control (RBAC).

  - Maintain automated audit trails and enforce strict data-retention policies.

  - Leverage scalable event-driven services for real-time stream processing.

  - Embed automated testing routines within an end-to-end CI/CD delivery framework.

  - Uphold ethical, privacy, and regulatory governance standards natively.

### Key Stakeholders and Responsibilities:

  - Store Operations Manager: Consumes live floor analytics to optimize staff allocation and shelf replenishment.

  - Retail Data Analyst: Analyzes aggregated, anonymized trends to evaluate product demand without accessing raw identities.

  - Compliance & Privacy Officer: Governs retention schedules, audits access logs, and validates privacy-policy adherence.

  - DevOps / Platform Engineer: Builds and maintains event-driven message brokers, monitoring systems, and automated CI/CD pipelines.

  - Retail Customer (Indirect Stakeholder): Experiences optimized store layout and service without sacrificing personal privacy or device identities.

- Create Epics and User Stories

### Epic 1: Edge Ingestion & PII Minimization (PPA)

  - US-PPA-01: As a Data Privacy Officer, I want edge sensor payloads to be cryptographically hashed and stripped of device MAC and IP addresses before transmission, so that customer privacy is guaranteed at the ingestion layer.

  - US-PPA-02: As a Platform Security Admin, I want the ingestion gateway to validate and reject unanonymized packets, so that unmasked PII never enters the processing stream.

### Epic 2: Scalable Real-Time Event Processing (EDP)

  - US-EDP-01: As a Retail Data Analyst, I want customer movement events processed through a distributed event broker in real time, so that live zone-occupancy metrics are calculated with sub-second latency.

  - US-EDP-02: As a Store Operations Manager, I want shelf interaction events linked with real-time stock counters, so that high-demand products nearing depletion trigger automated restock alerts.

### Epic 3: Operational Dashboards & Secure APIs (ODS)

  - US-ODS-01: As a Store Operations Manager, I want an interactive live heat-map dashboard, so that I can visualize foot-traffic bottlenecks and redirect store associates.

  - US-ODS-02: As a Platform Security Admin, I want role-based access control (RBAC) enforced across all analytics APIs, so that sensitive operational data is restricted to authorized personnel.

### Epic 4: Compliance, Audit & Automated Delivery (CAD)

  - US-CAD-01: As a Compliance Officer, I want automated data-retention policies to permanently purge raw event logs after 30 days, so that organizational liability is minimized.

  - US-CAD-02: As a DevOps Engineer, I want CI/CD pipelines executing automated tests and security scans on every commit, so that new features deploy reliably with zero downtime.

- Define Acceptance Criteria

### US-PPA-01: Edge Anonymization

  - Given raw sensor payloads containing device hardware identifiers (MAC/IP addresses),

  - When the ingestion pipeline receives the payload at the edge gateway,

  - Then the identifier must be converted using a salted SHA-256 one-way cryptographic hash with rotating daily keys,

  - And raw identifiers must be cleared from volatile memory without ever being written to persistent storage.

### US-EDP-01: Real-Time Stream Processing

  - Given an active stream of anonymized zone-transition events published to the message broker,

  - When retail traffic volume spikes up to 10,000 events per second,

  - Then the stream processor must aggregate zone occupancy and dwell metrics within an end-to-end latency of under 500 milliseconds,

  - And zero event loss must occur during horizontal scaling transitions.

### US-ODS-02: Role-Based Access Control (RBAC)

  - Given an incoming API request to access store analytics endpoints,

  - When the client sends a request with an authentication JWT bearer token,

  - Then the API gateway must validate the token signature and enforce endpoint permission policies,

  - And unauthorized requests must immediately return HTTP 403 Forbidden and record an audit log event.

### US-CAD-01: Automated Data-Retention Purging

  - Given historical telemetry records stored in the primary datastore,

  - When a daily automated lifecycle worker executes at midnight,

  - Then raw event records with a timestamp older than 30 days must be permanently deleted,

  - And a cryptographic audit summary of purged record counts must be recorded in the audit log.

- Prioritize the Product Backlog

The product backlog is prioritized using the MoSCoW framework, factoring in architectural dependencies, data privacy compliance, and immediate business value:

| Story ID | User Story Summary | Priority | Dependencies | Value Rationale |
| --- | --- | --- | --- | --- |
| US-PPA-01 | Cryptographic Edge Hashing & PII Stripping | Must Have | None | Essential privacy gatekeeper; unmasked data cannot enter the stream. |
| US-PPA-02 | Ingestion Invalidation & Gatekeeper Rejection | Must Have | US-PPA-01 | Guarantees downstream compliance and eliminates legal risk. |
| US-EDP-01 | Distributed Stream Processing Engine | Must Have | US-PPA-01 | Core pipeline for real-time operational calculations. |
| US-ODS-02 | API Gateway Authentication & RBAC | Must Have | None | Critical access security preventing unauthorized internal exposure. |
| US-CAD-02 | Automated CI/CD Pipeline & Automated Testing | Must Have | None | Foundation for reliable development and regression testing. |
| US-ODS-01 | Interactive Store Heat-Map Dashboard | Should Have | US-EDP-01, US-ODS-02 | Delivers visual operational visibility to store managers. |
| US-EDP-02 | Shelf Sensor Restock Trigger Integration | Should Have | US-EDP-01 | Automates stockout prevention and inventory control. |
| US-CAD-01 | Automated Data-Retention Lifecycle Purging | Should Have | US-EDP-01 | Enforces long-term storage governance schedules. |

- Plan the Sprint Backlog (Sprint 1)

Sprint 1 focuses on establishing the secure edge-ingestion pipeline, real-time message streaming broker, automated CI/CD pipeline, and fundamental RBAC enforcement:

| Story ID | Selected User Story | Actionable Technical Tasks Breakdown | Task Est. |
| --- | --- | --- | --- |
| US-PPA-01 | Cryptographic Edge Hashing & PII Stripping | - Implement edge gateway payload parser in Go/Python. - Integrate SHA-256 salting service with daily rotating keys. - Build in-memory payload sanitizer and purge raw cache. | 5 hrs 6 hrs 4 hrs |
| US-PPA-02 | Ingestion Invalidation & PII Rejection | - Define JSON schema validation rules for incoming telemetry. - Add automated dead-letter-queue (DLQ) routing for non-compliant payloads. | 4 hrs 4 hrs |
| US-EDP-01 | Real-Time Event Stream Broker | - Deploy distributed Apache Kafka cluster with topic partitions. - Implement stream processor to calculate rolling dwell metrics. - Execute load testing up to 10,000 events/sec. | 6 hrs 8 hrs 5 hrs |
| US-ODS-02 | API Authentication & RBAC | - Configure OAuth2/JWT middleware on the API gateway. - Implement role-based route guards (StoreManager vs Analyst). - Add automated audit log writes for unauthorized requests. | 5 hrs 4 hrs 3 hrs |
| US-CAD-02 | Automated CI/CD & Testing | - Build GitHub Actions / GitLab CI pipeline script. - Integrate automated unit test runner and SonarQube code scan. - Configure automated deployment to staging Kubernetes cluster. | 4 hrs 4 hrs 5 hrs |

- Estimate Effort Using Story Points

Effort is estimated using Planning Poker with the standard Fibonacci sequence (1, 2, 3, 5, 8, 13) based on implementation complexity, uncertainty, and regulatory risk:

| Story ID | User Story | Points | Estimation Justification |
| --- | --- | --- | --- |
| US-PPA-01 | Edge Hashing & PII Stripping | 5 | Moderate complexity; requires cryptographic key rotation and strict memory isolation. |
| US-PPA-02 | Ingestion Gatekeeper Rejection | 3 | Straightforward schema validation rules and dead-letter queue routing. |
| US-EDP-01 | Real-Time Event Stream Broker | 8 | High complexity; requires distributed event streaming setup, partition tuning, and latency optimization under high load. |
| US-ODS-02 | API Authentication & RBAC | 5 | Standard OAuth2/JWT implementation, but requires custom audit trail logging hooks. |
| US-CAD-02 | Automated CI/CD & Testing | 5 | Moderate effort to configure multi-stage automated pipelines and containerized testing. |

Total Sprint 1 Story Points: 26 Story Points (Planned for a cross-functional Scrum team of 5 engineers over a 2-week sprint cycle).

- Present the Sprint Goal and Expected Deliverables

Sprint Goal: "Deliver a fully automated, secure, and privacy-preserving data ingestion and streaming pipeline that ingests anonymized telemetry, computes dwell metrics in real time via an event broker, and passes automated security and regression checks via CI/CD."

### Expected Sprint Deliverables:

  - Edge Anonymization Gateway: Operational service that pseudonymizes MAC/IP addresses with salted SHA-256 prior to streaming.

  - Event Streaming Infrastructure: Configured distributed message broker capable of processing up to 10,000 anonymized events/second with sub-500ms latency.

  - Secure API Gateway: Protected endpoints enforcing JWT validation, RBAC route guarding, and unauthorized audit logging.

  - Automated CI/CD Pipeline: Fully functional deployment pipeline executing unit test suites, integration tests, and security scans on every pull request.

  - Sprint Documentation & Verification: Completed test coverage report (>= 85% code coverage) and validated acceptance criteria sign-offs for all 5 sprint backlog stories.

Rubrics for Calculation

| Criteria | Excellent (5 Marks) | Good (3 Marks) | Satisfactory (2 Marks) | Needs Improvement (1 Mark) |
| --- | --- | --- | --- | --- |
| Project Vision & Stakeholder Identification (30%) | Project vision is clear, comprehensive, and aligned with the problem statement. All relevant stakeholders and their roles are correctly identified. | Vision is clear with minor omissions. Most stakeholders are correctly identified. | Vision is partially defined. Some stakeholders are missing or incorrectly identified. | Vision is unclear or incomplete. Stakeholders are poorly identified or missing. |
| Epics & User Stories (25%) | Epics are well-defined and user stories are complete, follow Agile format, and fully capture functional requirements. | Epics and user stories are mostly complete with minor formatting or requirement issues. | User stories are partially complete with limited Agile structure. | User stories are incomplete, unclear, or do not follow Agile practices. |
| Acceptance Criteria (20%) | Acceptance criteria are specific, measurable, testable, and aligned with all user stories. | Acceptance criteria are mostly clear and testable with minor gaps. | Acceptance criteria are partially defined and lack clarity or completeness. | Acceptance criteria are missing or not aligned with user stories. |
| Product Backlog Prioritization & Sprint Planning (15%) | Product backlog is logically prioritized, sprint backlog is realistic, and task breakdown is complete. | Backlog prioritization and sprint planning are mostly appropriate with minor issues. | Prioritization or sprint planning is partially complete with limited justification. | Backlog prioritization and sprint planning are poorly organized or incomplete. |
| Story Point Estimation, Sprint Goal & Presentation (10%) | Story point estimation is well justified, sprint goal is clear, deliverables are realistic, and presentation is professional and well organized. | Estimation and sprint goal are mostly appropriate with minor inconsistencies. Presentation is clear. | Estimation or sprint goal lacks justification. Presentation is adequate but incomplete. | Estimation is unrealistic or missing. Sprint goal, deliverables, and presentation are unclear or incomplete. |

| Criteria | Mark |
| --- | --- |
| Project Vision & Stakeholder Identification (30%) | /5 |
| Epics & User Stories (25%) | /5 |
| Acceptance Criteria (20%) | /5 |
| Product Backlog Prioritization & Sprint Planning (15%) | /5 |
| Story Point Estimation, Sprint Goal & Presentation (10%) | /5 |
| TOTAL | /25 |